## Sheet1
Date | Activity | Time
2020-05-02 | Reviewing DialogFlow Documentation | 22:30-01:30 | 2.5
2020-05-03 | Creating dialogflow agent and setting up the API authentication | 22:00-01:00 | 3
2020-05-04 | Reading documentation and tutorials on Dialogflow project structure | 22:45-01:30 | 2.75
2020-05-05 | Setting up repository and planning structure of app | 22:30-01:00 | 2.5
2020-05-06 | Writing automation for extraction of questions and answers from provided document | 22:30-01:00 | 2.5
2020-05-07 | Reviewing the Python API and setting up automation of uploading Intents | 22:45-01:30 | 2.75
2020-05-08 | Scripting the automation of uploading Intents | 22:45-01:00 | 2.25
2020-05-09 | Scripting the automation of uploading Intents | 22:30-01:00 | 2.5
2020-05-22 | Rewriting the script because the earlier method did not work | 22:30-12:30 | 2
2020-05-11 | Writing new script for automation | 11:30-01:30 | 2
2020-05-12 | Writing new script for automation | 22:45-01:00 | 2.25
2020-05-13 | Fixing bugs in the automation script and reviewing the API docs | 22:00-01:00 | 3
2020-05-14 | Fixing bugs in the automation script and reviewing the API docs | 22:30-01:00 | 3
2020-05-15 | Fixing authentication errors and testing the bot | 18:00-19:00 | 1
2020-05-16 | Reviewing various frameworks for the frontend (Rasa, Django) | 22:00-12:00 | 2
2020-05-17 | Researching ways to achieve this in vanilla Javascript | 22:00-12:00 | 2
2020-05-18 | Reading documentation and tutorials for communication with DialogFlow | 22:30-12:30 | 2
2020-05-19 | Writing Python script for communication with DialogFlow Server
2020-05-20 | Setting up website template for frontend | 22:30-01:00 | 2.5
2020-05-21 | Reading documentation on Javascript file handling and setting up Django project | 22:00-12:00 | 2
2020-05-22 | Writing the script for receiving input from user | 22:30-01:00 | 2.5
2020-05-23 | Writing Django views and AJAX requests | 23:30-01:00 | 1.5
2020-05-24 | Writing Django views and AJAX requests | 15:00-19:00 | 4